## Sheet0
ID | Project ID | Project Name | Key ID | Key | Issue Type ID | Issue Type | Category ID | Category Name | Version ID | Version | Subject | Description | Status ID | Status | Priority ID | Priority | Milestone ID | Milestone | Resolution ID | Resolution | Assignee ID | Assignee | Create User ID | Created by | Created Date | Due date | Update User ID | Updated by | Updated | Attachment | Shared File | Comment1
3652345 | 68465 | ATM Project | 7 | ATM_1-7 | 293215 | Bug |  |  | 64070 | 1.1 | (Exploratory Testing) Balance Inquiry Functionality, Version 1.0 | * Either Card #1 or Card #2 Inserted. System on idle * Testing the Balance Inquiry Function with Card #1 and Card #2 * When using the Balance Inquiry function, the ATM terminal only gives you the option to view the balance of two accounts for both cards, the Checking account, and Money Market account, but not the Savings account for Card #1 * On Card #1 and #2, inquiring about the balance of the checking account works fine. * But when inquiring about the money market account we get two issues * On Card #1, there isn’t supposed to be a money market account and when you do choose to inquire about the money market account, the receipt shows you the balance of the Savings account instead. The account shown on the terminal is mislabeled and should say Savings instead of Money Market * On Card #2, there is a money market account but, the ATM terminal says that it is an “Invalid Account Type”, even though Card #2 should have a money market account * Steps to reproduce defect/bug * Insert Card #1 or #2 and enter the appropriate PIN associated (42 and 1234 respectively) * Enter the amount of $20 bills that the atm will have * Select “Balance Inquiry” as transaction type *Select the “Money Market” account when asked which account you want to inquire about * Expected output *For Card #1, when selecting balance inquiry, the two accounts available should be the Checking and Savings accounts * For Card #2, when you select the Money Market account, it should output $5000 | 3 | Resolved | 3 | Normal |  |  |  |  | 320105 | Ivan Lou Tompong | 320105 | Ivan Lou Tompong | Jan. 26, 2022 21:26 |  | 320105 | Ivan Lou Tompong | Jan. 28, 2022 20:31 | 0 | 0
3657593 | 68465 | ATM Project | 18 | ATM_1-18 | 293215 | Bug |  |  | 64070 | 1.1 | (Regression Testing) ATM terminal shows an error screen when performing balance inquiry about Savings account on Card #1 | *Testing Balance Inquiry functionality * System is waiting for user to pick which account on card #1 to inquire about * Steps to reproduce: * Turn on ATM * Insert card #1 and enter the PIN (42) * Choose "Balance Inquiry" as transaction type * Choose "Savings" when prompted to choose an account to inquire about * Terminal is expected to be blank while the Log shows the type of transaction made and the receipt shows the type of transaction and the account balance * Terminal displays "Unknown Error" instead of being blank, while the Log shows the type of transaction made and the receipt shows the type of transaction and the account balance | 1 | Open | 3 | Normal |  |  |  |  | 320105 | Ivan Lou Tompong | 320105 | Ivan Lou Tompong | Jan. 28, 2022 19:48 |  | 320105 | Ivan Lou Tompong | Jan. 28, 2022 20:31 | 0 | 0
3652300 | 68465 | ATM Project | 4 | ATM_1-4 | 293215 | Bug |  |  | 64070 | 1.1 | (Exploratory Testing) Withdrawal Functionality Version 1.0 | *Testing the 'Withdrawal' functionality of the system * Card #1 or #2 is inserted. The System is on and on idle, waiting to select transaction type * The checking, savings and money market accounts assumed to contain an initial amount of $100, $1000, and $5000 respectively for each withdrawal tested * The amount of money withdrawn from account when a button is pushed does not match the amount associated with that button i.e.: • Withdrawing $20 causes a withdrawal of $40 instead • Withdrawing $40 causes a withdrawal of $60 instead • Withdrawing $200 causes a withdrawal of $20 instead • Withdrawing $60 causes a withdrawal of $100 instead • Withdrawing $100 causes a withdrawal of $200 instead *Steps to reproduce defect/bug • Insert Card #1 or #2 and enter the appropriate PIN associated (42 and 1234 respectively) • Enter the amount of $20 bills that the atm will have •If the amount of $20 bills is not enough to cover the withdrawal amount, then it is a failed transaction •i.e., if you withdraw $80 and there is only two $20 bills then the transaction fails • Select ‘Withdraw’ as the transaction type • Select ‘Checking account’ • Choose what amount of money to withdraw * The expected outcome is that whatever amount of money was chosen to be withdrawn, the Log would say that amount of money was withdrawn, and the receipt would show the correct amount of money was withdrawn along with the Total Balance left in the checking account * The actual outcome was that the Log would say that a different amount of money than what was specified was withdrawn and the receipt would show the same thing. | 3 | Resolved | 3 | Normal |  |  |  |  | 320105 | Ivan Lou Tompong | 320105 | Ivan Lou Tompong | Jan. 26, 2022 21:16 |  | 320105 | Ivan Lou Tompong | Jan. 28, 2022 20:31 | 0 | 0
3652401 | 68465 | ATM Project | 12 | ATM_1-12 | 293215 | Bug |  |  | 64070 | 1.1 | (MFT) Test Case #6, Version 1.0 | * Functionality: if System rejects an unreadable card * Initial State: the System is on and not servicing a customer * Steps to recreate bug/defect: * Turn on System * Enter a legitimate amount of $20 dollar bills the ATM starts with * Insert a card * Specify a card number that doesn't exit when asked to enter the card number(Card #1 and Card #2 are supposed to be the only readable cards) * Expected Output: The card is ejected automatically and displays an error screen * Actual Output: The system accepts the card and asks to enter a pin, only when you enter a pin is the unreadable card then ejected. | 2 | In Progress | 3 | Normal |  |  |  |  | 320105 | Ivan Lou Tompong | 320105 | Ivan Lou Tompong | Jan. 26, 2022 21:51 |  | 320105 | Ivan Lou Tompong | Jan. 28, 2022 20:31 | 0 | 0 | Jan. 28, 2022 19:33 Ivan Lou Tompong Defect still exists in version 1.1
3652366 | 68465 | ATM Project | 9 | ATM_1-9 | 293215 | Bug |  |  | 64070 | 1.1 | (MFT) Test Case #3, Version 1.0 | *Functionality: Connection to the Bank is established * Initial State: System has just been turned on * Steps to reproduce bug/defect * Turn on system * Enter a legitimate amount of $20 bills the system ATM starts of with * Expected Output: The output should demonstrate that a connection to the bank has been established, either in the log or terminal. * Actual Output: The ATM immediately asks for a card to insert | 2 | In Progress | 3 | Normal |  |  |  |  | 320105 | Ivan Lou Tompong | 320105 | Ivan Lou Tompong | Jan. 26, 2022 21:38 |  | 320105 | Ivan Lou Tompong | Jan. 28, 2022 20:30 | 0 | 0 | Jan. 28, 2022 19:31 Ivan Lou Tompong Defect still exists in version 1.1
3657525 | 68465 | ATM Project | 17 | ATM_1-17 | 293215 | Bug |  |  | 64070 | 1.1 | [ET] Balance Inquiry outputs Unknown Error | Function being tested: Balance Inquiry of Savings Account Initial state of system: Valid Card and Pin have been entered into the ATM Steps: Enter Valid card # and pin, press 4 for balance inquiry Expected outcome: Receipt is printed with inquiry. Actual Outcome: Unknown error output to screen followed by a delayed receipt. | 1 | Open | 3 | Normal | [6 empty] | 320107 | Alex | Jan. 28, 2022 17:02 |  | 320107 | Alex | Jan. 28, 2022 17:02 | 0 | 0
3657452 | 68465 | ATM Project | 16 | ATM_1-16 | 293215 | Bug |  |  | 64070 | 1.1 | [ET] Wrong Label When Transferring from CHQ to SAV | Function being tested: Transfer funds Initial state of the system: Transfer option chosen, transferring from CHQ to SAV Steps to reproduce the defect/bug: - Turn on machine - Insert card - Card number: 1 - PIN: 42 - Choose (3) Transfer for transaction type - Transfer from CHQ, and then to SAV - Enter a valid amount Expected Outcome: Transfer certain amount of money from CHQ to SAV Actual outcome: Label says it is transferring money from SAV to CHQ | 1 | Open | 3 | Normal | [6 empty] | 320108 | John Cedric Acierto | Jan. 28, 2022 15:12 |  | 320108 | John Cedric Acierto | Jan. 28, 2022 15:12 | 0 | 0
3652263 | 68465 | ATM Project | 3 | ATM_1-3 | 293215 | Bug |  |  | 64070 | 1.1 | [ET] Entering valid PIN after invalid PIN | Function being tested: Entering valid PIN Initial state of system: System is on with card number chosen Steps: Insert card, enter correct card number, enter invalid PIN, enter valid PIN Expected outcome: After entering valid PIN, user should be able to select a transaction type Actual Outcome: After entering valid PIN, user is prompted to enter PIN again | 2 | In Progress | 3 | Normal | [6 empty] | 320106 | Dominic | Jan. 26, 2022 21:07 |  | 320106 | Dominic | Jan. 27, 2022 18:48 | 0 | 0
3652381 | 68465 | ATM Project | 10 | ATM_1-10 | 293215 | Bug |  |  | 64070 | 1.1 | [MFT] Unable to make savings account inquiry | Function being tested: System asks customer to choose an account to inquire about Initial State: System turned ON with card #1 or #2 inserted Steps: - Insert card - Enter card number - Enter valid PIN - Select "4" for balance inquiry - Select "2" for savings account Expected outcome: System displays savings account information Actual outcome (card 1): System displays "unknown error" and dispenses $500.00 Actual outcome (card 2): System displays "invalid account type" | 2 | In Progress | 3 | Normal | [6 empty] | 320106 | Dominic | Jan. 26, 2022 21:44 |  | 320106 | Dominic | Jan. 27, 2022 18:47 | 0 | 0
3652397 | 68465 | ATM Project | 11 | ATM_1-11 | 293215 | Bug |  |  | 64070 | 1.1 | [ET] Accessing balance inquiry for money market (Card 1) | Function being tested: Accessing balance inquiry for money market Initial state: System turned ON with card 1 inserted Steps: - Insert card 1 - Enter valid PIN (42) - Select "4" for balance inquiry - Select "2" for money market Expected outcome: System displays account balance and information on receipt Actual outcome: System displays "unknown error" and dispenses $500.00 This bug was resolved in version 1.1, however, actual outcome is now: System displays "invalid account type" | 2 | In Progress | 3 | Normal | [6 empty] | 320106 | Dominic | Jan. 26, 2022 21:50 |  | 320106 | Dominic | Jan. 27, 2022 18:41 | 0 | 0
3652432 | 68465 | ATM Project | 15 | ATM_1-15 | 293215 | Bug |  |  | 64070 | 1.1 | [ET] Accessing balance inquiry for money market (card 2) | Function being tested: Accessing balance inquiry for money market on card 2 Initial state: System is turned ON with card 2 inserted Steps: - Insert card - Enter card number (2) - Enter valid PIN (1234) - Select "4" for balance inquiry - Select "2" for money market Expected outcome: System displays account balance and information on receipt Actual outcome: System displays invalid account | 3 | Resolved | 3 | Normal | [6 empty] | 320106 | Dominic | Jan. 26, 2022 22:04 |  | 320106 | Dominic | Jan. 27, 2022 18:41 | 0 | 0
3652341 | 68465 | ATM Project | 6 | ATM_1-6 | 293215 | Bug |  |  | 64070 | 1.1 | [MFT] Entering valid PIN after invalid PIN twice | Function being tested: Correct re-entry of PIN on third try Initial State: ATM is on and card number has been entered Steps: Insert card, enter card number, enter invalid PIN, enter invalid PIN again, enter valid PIN Expected Outcome: User is prompted to choose a transaction type Actual Outcome: User is prompted to enter PIN again This bug exists in both version 1.0 and 1.1 | 2 | In Progress | 3 | Normal | [6 empty] | 320106 | Dominic | Jan. 26, 2022 21:25 |  | 320106 | Dominic | Jan. 27, 2022 18:37 | 0 | 0
3652314 | 68465 | ATM Project | 5 | ATM_1-5 | 293215 | Bug |  |  | 64013 | 1.0 | [ET] Depositing sum below 1$ to Checking Account outputs decreased initial sum ATM Program V1.0 | Function being tested: Depositing to checking account Initial state of system: Valid Card and Pin have been entered into the ATM Steps: Enter Valid card # and pin, press 2 to deposit, enter sum below 1$ Expected outcome: After depositing desired amount, checking account balance sum = initial balance + deposit Actual Outcome: After depositing desired amount, checking account balance sum = initial balance + deposit - 10$ 0.02$ Deposited: Wed Jan 26 21:10:25 MST 2022 First National Bank of Podunk ATM #42 Gordon College CARD 2 TRANS #7 DEPOSIT TO: CHKG AMOUNT: $0.02 TOTAL BAL: $90.02 AVAILABLE: $100.00 | 3 | Resolved | 2 | High | [6 empty] | 320107 | Alex | Jan. 26, 2022 21:20 |  | 320107 | Alex | Jan. 27, 2022 11:07 | 0 | 0 | Jan. 27, 2022 11:07 Alex Original issue resolved however has Test Case #22's bug
3652360 | 68465 | ATM Project | 8 | ATM_1-8 | 293215 | Bug |  |  | 64013 | 1.0 | [MFT] Test Case #22 - Deposit to Any Account results in incorrect balance | Function Being Tested: System Performs a legitimate deposit transaction properly Initial State of System: System is requesting that customer insert an envelope Steps to reproduce defect/bug: Enter valid card # and pin, select deposit, enter valid integer, click enter, insert envelope Expected Outcome: Account balance = initial balance + deposit value Actual Outcome: Account balance = initial balance + deposit value - 10$ | 2 | In Progress | 3 | Normal | [6 empty] | 320107 | Alex | Jan. 26, 2022 21:35 |  | 320107 | Alex | Jan. 27, 2022 11:04 | 0 | 0 | Jan. 27, 2022 11:04 Alex Defect still exists in version 1.1
3652417 | 68465 | ATM Project | 14 | ATM_1-14 | 293215 | Bug |  |  | 64013 | 1.0 | [MFT] Test Case #29 - Transfer to Any Account results in incorrect updated balance | Function Being Tested: System Performs a legitimate transfer transaction properly Initial State of System: System is displaying a request for the customer to type a dollar amount Steps to reproduce defect/bug: Enter valid card # and pin, select transfer, enter valid amount to transfer, click enter, view receipt Expected Outcome: Receiving accounts updated balance = initial balance + transferred value Actual Outcome: Receiving accounts updated balance = initial balance + transferred value - 0.50$ | 3 | Resolved | 3 | Normal | [6 empty] | 320107 | Alex | Jan. 26, 2022 21:57 |  | 320107 | Alex | Jan. 27, 2022 11:00 | 0 | 0
3652405 | 68465 | ATM Project | 13 | ATM_1-13 | 293215 | Bug |  |  |  |  | MFT: System does not ask customer for a different withdrawal amount when funds are insufficient | Function being tested: System verifies that it has sufficient cash in hand to fulfill the request The initial state of the system: system has been started up with less than the maximum withdrawal amount in cash on hand; system is requesting a withdrawal amount Steps to reproduce the defect: - enter 10 for the amount of $20 bills on startup - Choose Card 1 - Enter PIN correctly - Withdraw some money (choose a small amount) - Withdraw another amount of money (bigger than the AVAILABLE amount) Expected outcome: System displays an appropriate message and asks customer to choose a different amount. Actual outcome: System displays an appropriate message (insufficient available balance) but does not ask customer to choose a different amount. It asks the customer whether they would like to do another transaction. | 1 | Open | 3 | Normal | [6 empty] | 320108 | John Cedric Acierto | Jan. 26, 2022 21:53 |  | 320108 | John Cedric Acierto | Jan. 26, 2022 21:53 | 0 | 0
3652262 | 68465 | ATM Project | 2 | ATM_1-2 | 293215 | Bug |  |  |  |  | [ET] Inaccurate Amount Transferred Within Accounts | [ET] Inaccurate Amount Transferred Within Accounts Function being tested: transfer from CHQ to SAV The initial state of the system: system is on and is currently serving a customer Steps to reproduce the defect/bug: - insert card - put in correct card number and PIN - transfer from CHQ to SAV - enter $10.00 for the amount Expected outcome: $10.00 transferred into SAV Actual outcome: $9.50 transferred into SAV | 1 | Open | 3 | Normal | [6 empty] | 320108 | John Cedric Acierto | Jan. 26, 2022 21:06 |  | 320108 | John Cedric Acierto | Jan. 26, 2022 21:06 | 0 | 0
3652257 | 68465 | ATM Project | 1 | ATM_1-1 | 293216 | Task |  |  |  |  | [ET] Inaccurate Amount Transferred Within Accounts | Function being tested: transfer from CHQ to SAV The initial state of the system: system is on and is currently serving a customer Steps to reproduce the defect/bug: - insert card - put in correct card number and PIN - transfer from CHQ to SAV - enter $10.00 for the amount Expected outcome: $10.00 transferred into SAV Actual outcome: $9.50 transferred into SAV | 1 | Open | 3 | Normal | [6 empty] | 320108 | John Cedric Acierto | Jan. 26, 2022 21:04 |  | 320108 | John Cedric Acierto | Jan. 26, 2022 21:04 | 0 | 0